## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Colorado Technical University, CS491
| Project | Bookstore Management System
| Product Owner | Damian Jay Moore
| Scrum Master | Damian Jay Moore
| Development Team | Damian Jay Moore
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
BMS-1 | Manage Book Inventory Records | As a store employee, I want to store each book's title, author, ISBN/UUID, price, quantity, and shelf location, so that I can replace the paper stock cards. | All six fields listed in the source text can be entered and viewed. Records can be edited and deleted. | 1
BMS-2 | Automatic Stock Quantity Updates | As a store employee, I want book quantities to update automatically when books are sold or received, so that inventory counts stay accurate without manual recalculation. | Quantity decreases on sale. Quantity increases on receiving stock. No manual quantity entry required. | 2
BMS-3 | Checkout Calculation (Totals, Tax, Change) | As a cashier, I want the system to calculate the subtotal, tax, and change owed, so that I can complete a customer transaction accurately. | Subtotal, tax, and total are calculated correctly. Change due is calculated for cash payments. Ties directly to Definition of Done requirement: "accurate tax and total calculations." | 3
BMS-4 | Daily Cash/Card Sales Log | As a store owner, I want a log of all daily cash and card sales, so that I can review revenue. | Every sale records date, time, amount, and payment method. A daily total can be viewed. | 4
BMS-5 | Supplier Order Tracking | As a store owner, I want to track incoming book orders from suppliers, so that I know what stock is on the way. | An order can be logged with supplier, books ordered, and status. Status can be updated to received. | 5
BMS-6 | Customer Special Order Requests | As a cashier, I want to log a customer's request for an out-of-stock book, so that we can order it and notify them. | Request logs customer name, contact info, and book requested. Status can be updated (ordered/fulfilled). | 6
BMS-7 | User Login and Access Control | As a store owner, I want each staff member to have their own login, so that only authorized people can use the system. | Each user has a unique login. Unauthenticated users cannot access the system. | 7
BMS-8 | Protect Sales and Customer Data | As a store owner, I want sales records and customer information protected, so that sensitive data isn't exposed. | Sales and customer data are not stored in plain readable text where avoidable. Only authorized staff can view records. | 8

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Bookstore Management System
|  | Sprint # |  | 1
|  | Start date |  | 2026-09-06
|  |  | Total Team Members | 1
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19
T1 | BMS-1 | Design database schema for book records (title, author, ISBN, price, quantity, shelf location) |  | 8
T2 | BMS-1 | Build form to add/edit book records |  | 12
T3 | BMS-1 | Build search/view function for book records |  | 8
T4 | BMS-2 | Build login screen and session handling — restricts access to protect financial and customer data |  | 10
T5 | BMS-2 | Design user accounts table and authentication logic |  | 8
T6 | BMS-2 | Restrict system access to authenticated users only |  | 6
T7 | BMS-3 | Build subtotal calculation logic |  | 6
T8 | BMS-3 | Build tax calculation logic |  | 4
T9 | BMS-3 | Build change-due calculation for cash payments |  | 4
T10 | BMS-4 | Link checkout completion to automatic inventory decrement |  | 6
T11 | BMS-4 | Link supplier receiving action to automatic inventory increment |  | 6
T12 | — | Sprint 1 planning meeting |  | 2
T13 | — | Daily standups (10 working days) |  | 5
T14 | — | Set up development infrastructure (GitHub repo, database server) |  | 8
T15 | — | Sprint 1 review/demo |  | 2
T16 | — | Sprint 1 retrospective |  | 1
|  | Remaining units (actual) |  | 16 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 14.8571 | 13.7143 | 12.5714 | 11.4286 | 10.2857 | 9.1429 | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0
[10 empty] | 0 | 66 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Bookstore Management System
|  | Sprint # |  | 2
|  | Start date |  | 2026-09-06
|  |  | Total Team Members | 1
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19
T1 | BMS-5 | Design sales transaction record schema |  | 6
T2 | BMS-5 | Build daily sales log view |  | 8
T3 | BMS-5 | Build daily sales total calculation |  | 4
T4 | BMS-6 | Design supplier order schema |  | 6
T5 | BMS-6 | Build create/view function for supplier orders |  | 8
T6 | BMS-6 | Build order status update (pending/received) |  | 6
T7 | BMS-7 | Implement protection for stored sales/customer data — addresses data privacy and breach-prevention obligations |  | 8
T8 | BMS-7 | Restrict sales/customer data views to authorized roles |  | 6
T9 | BMS-7 | Set up data backup process — supports data retention and recovery obligations |  | 4
T10 | BMS-8 | Build customer request logging form — collects only necessary personal data (name, contact info) |  | 8
T11 | BMS-8 | Build request status update (ordered/fulfilled) |  | 6
T12 | — | Sprint 2 planning meeting |  | 2
T13 | — | Daily standups (10 working days) |  | 5
T14 | — | Sprint 2 review/demo |  | 2
T15 | — | Sprint 2 retrospective |  | 1
|  | Remaining units (actual) |  | 16 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 14.8571 | 13.7143 | 12.5714 | 11.4286 | 10.2857 | 9.1429 | 8 | 6.8571 | 5.7143 | 4.5714 | 3.4286 | 2.2857 | 1.1429 | 0
[10 empty] | 0 | 56 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0